## Sheet1
Task | Subtask | Priority | Dev Effort | Test Effort
Create conversion method to convert v1.0 assessment save data to v2.0 |  | Required | Medium | High
Complete continuum CMS changes (component reordering) |  | Required | Low | Low
Create continuum v2.0 change log page (revealed on upgrade and accessible from the support page) |  | Required | Medium | Low
Add numbers to the indicator page nav links |  | High | Low | Low
Add training to site search |  | High | Low | Low
Rename ASD-X to Test District |  | High | Low | Low
Move summary charts to the top of the report |  | High | Low | Low
Preserve Big Seven navigation on small screens (combine with on page nav) |  | High | Medium | Medium
Redesign assessment to report workflow | Review assessment toolbar iconography | High | Medium | Low
Redesign assessment to report workflow | Preserve assessment toolbar on report page (conditionally showing appropriate buttons) | High | High | High
Redesign assessment to report workflow | Create a download dialog for the report page (including explanatory text on which filetype to download) | High | High | Medium
Redesign assessment to report workflow | Merge active assessment and active report assessment (so there is only one assessment open at any time) | High | Medium | Medium
Open pdfs, images, and external websites in new tabs (including screen reader text) |  | High | Low | Low
Redesign collaboration workflow | Investigate benefits or restricting save function to single option (file) | Medium | Medium | Low
Redesign collaboration workflow | Provide clear instructions on how users can collaborate and best practice to avoid data loss | Medium | Medium | Low
Redesign collaboration workflow | Investigate URL-based save states for easier collaboration | Medium | High | High
Improve text for clarity and user experience | Improve change status dialog text | Medium | Low | Low
Improve text for clarity and user experience | Improve manage assessors dialog text to clarify purpose and limitations of adding assessors | Medium | Low | Low
Improve text for clarity and user experience | Improve search dialog text to clarify what is searchable | Medium | Low | Low
Improve text for clarity and user experience | Improve change status (complet to in progress) dialgo to include the assessment's reporting year and prompt whether the user wants to duplicate instead | Medium | Low | Low
Create a glossary popup for glossary term definitions |  | Low | High | High
Add a new chart to the report that shows how many components out of 30 are in each phase (e.g., stacked bar chart, simple numbers) |  | Low | High | Medium
Investigate returning user to exact list position in search dialog after closing a media dialog |  | Low | Medium | Medium